## Sheet1
TypeKey | UniqueKey | Item | PK | RelatedTo | Sort | StartDate | DueDate | Role | Setting1 | Setting2 | Description | Role2 | Role3
TemplateName |  | CLIENT - Corporate Tax Return | [8 empty] | Work with WestlakeTax to file our Corporate return
TemplateVersion |  | 1.0a
ImageURL |  | http://images.lifespace.com/portals/0/brands/westlaketax/Tax.png
TemplateKey |  | LifeSpace.Finance
Waiver
TemplateType |  | KeyDate
Variable | KeyDate | File Date: | [6 empty] | Date |  | When does this goal start?
Role | Responsible | Client: | [6 empty] | View |  | Who is the Client?
Role | Coach | Accountant: | [6 empty] | Admin |  | Who is the Accountant?
Community |  |  | 370636
Summary | Contact | About Westlake Tax |  |  |  | 0 | 0
Content |  |  | 679034 | Contact | [6 empty] | http://www.lifespace.com/Content.aspx?ID=679034
Summary | Preparation | Prepare Documentation |  |  |  | 0 | 6
Action |  | Gather E-Organizer, accounting files and documents |  | Preparation |  | -75 | -60 | Client |  |  | Gather all materials required to be sent to Westlake Tax including the E-Organizer file, accounting files, reports, government paperwork and other documents used for tax preparation
Action |  | Receive all materials from Client |  | Preparation |  | -60 | -60 | Coach |  |  | Receive paperwork from client and schedule Accountant/Staff
Action |  | Schedule preliminary review with Client |  | Preparation |  | -46 | -46 | Coach |  |  | Schedule review with client
Summary | Filing | File Return with IRS |  |  |  | -6 | 0
Action |  | File Return or Extensions |  | Filing |  | -6 | -6 | Coach |  |  | File the return or process an extension
Action |  | Schedule follow-up tasks |  | Filing |  | -6 | -6 | Coach |  |  | Schedule a follow-up with client. Create tasks and alter dates for these items within their project
Summary | FollowUp | Client Follow-up |  |  |  | 28 | 28
Action |  | Perform follow-up or close the file |  | FollowUp |  | 28 | 28 | Coach |  |  | Perform the follow-up tasks or mark this project complete